## EAC Data
| 2018-01-01 | 2018-02-01 | 2018-03-01 | 2018-04-01 | 2018-05-01 | 2018-06-01 | 2018-07-01 | 2018-08-01 | 2018-09-01 | 2018-10-01 | 2018-11-01 | 2018-12-01 | 2019-01-01 | 2019-02-01 | 2019-03-01 | 2019-04-01
As Sold Cost | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000
As Sold Revenue | 1250 | 1250 | 1250 | 1250 | 1250 | 1250 | 1250 | 1250 | 1250 | 1250 | 1250 | 1250 | 1250 | 1250 | 1250 | 1250
As Sold GP $ | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250
ITD Cost | 2018-01-01: 80; 2018-02-01: 140; 2018-03-01: 200; 2018-04-01: 260; 2018-05-01: 320; 2018-06-01: 380; 2018-07-01: 440; 2018-08-01: 500
ITD Revenue | 2018-01-01: 110; 2018-02-01: 200; 2018-03-01: 290; 2018-04-01: 380; 2018-05-01: 470; 2018-06-01: 560; 2018-07-01: 650; 2018-08-01: 740
ITD GP $ | 2018-01-01: 30; 2018-02-01: 60; 2018-03-01: 90; 2018-04-01: 120; 2018-05-01: 150; 2018-06-01: 180; 2018-07-01: 210; 2018-08-01: 240
EAC Cost | 2018-08-01: 500; 2018-09-01: 525; 2018-10-01: 600; 2018-11-01: 675; 2018-12-01: 775; 2019-01-01: 850; 2019-02-01: 900; 2019-03-01: 925; 2019-04-01: 975
EAC Revenue | 2018-08-01: 740; 2018-09-01: 725; 2018-10-01: 800; 2018-11-01: 850; 2018-12-01: 950; 2019-01-01: 1050; 2019-02-01: 1100; 2019-03-01: 1200; 2019-04-01: 1250
EAC GP $ | 2018-08-01: 240; 2018-09-01: 200; 2018-10-01: 200; 2018-11-01: 175; 2018-12-01: 175; 2019-01-01: 200; 2019-02-01: 200; 2019-03-01: 275; 2019-04-01: 275
Note the following definitions:
As Sold Cost - this is the total cost as per contract including additional CNs, etc.
As Sold Revenue - this is the total revenue agreed to with the customer on all signed contracts, POs and CNs.
As Sold GP $ - this is the difference between the As Sold Revenue and the As Sold Cost
ITD Cost - this is the cumulative cost incurred to date on the project
ITD Revenue - this is the cumulative revenue recognized to date on the project
ITD GP $ - this is the cumulative GP realized to date on the project (the difference between ITD Revenue and ITD Cost)
EAC Cost - this is the projected estimate of the remaining cumulative cost burn rate on the job.
EAC Revenue - this is the projected estimate of the remaining cumulative revenue recognition on the job.
EAC GP $ - this is the projected estimate of the cumulative GP remaining to be recognized (the difference between EAC Revenue and EAC Cost)