## Financial Performance
Financial Performance |  |  |  | Approved Budget by Category
| As Sold Budget (original contract value) | Revenue | 37014.096 |  | Revenue | Cost | GP | GP%
|  | Cost | 28503.539 | Approved Budget
|  | GP | 22.99% | Hourly Services | 36240.543 | 26586.757 | 9653.786 | 26.64%
| Approved Budget | Revenue | 57513 | <<company name>> Product | 12452.867 | 6466.087 | 5986.78 | 48.08%
| (Contract + all change notices) | Cost | 40274 | 3rd Party Goods and Services | 7367.609 | 6142.891 | 1224.718 | 16.62%
|  | GP | 29.97% | Expenses | 1452.731 | 1079 | 373.731 | 25.73%
| EAC Budget | Revenue | 57513.75 | Total Budget | 57513.75 | 40274.735 | 17239.015 | 29.97%
| (Total expected project value which would include | Cost | 40674.674 | - | 0 | 0
| projected changes that ay not yet be approved | GP | 29.28% | ITD Actual
| Actual ITD (what the project has Incurred To Date) | Revenue | 55504 | Hourly Services | 34904.498 | 25605.85 | 9298.648 | 26.64%
|  | Cost | 38840 | <<company name>> Product | 12324.702 | 6382.731 | 5941.971 | 48.21%
|  | GP | 30.02% | 3rd Party Goods and Services | 6906.689 | 5850.346 | 1056.343 | 15.29%
| Backlog | Revenue | 2009 | Expenses | 1369.108 | 1001 | 368.108 | 26.89%
| (Approved Budget less Actual ITD) | Cost | 1434 | Total Actuals | 55504.997 | 38839.927 | 16665.07 | 30.02%
|  | GP | 28.62% | - | 0 | 0
Estimate to Complete
| Invoiced To Date (excluding DRAFT invoices) |  | 54786.2951 | Hourly Services | 1336.045 | 980.907 | 355.138 | 26.58%
| Unbilled Revenue |  | 717.7049 | <<company name>> Product | 128.165 | 83.356 | 44.809 | 34.96%
| Invoice Backlog |  |  | 3rd Party Goods and Services | 460.92 | 292.545 | 168.375 | 36.53%
| % Invoiced to Approved Budget |  | 95.26% | Expenses | 83.623 | 78 | 5.623 | 6.724%
| % of Costs Completed |  | 96.44% | Total ETC | 2008.753 | 1434.808 | 573.945 | 28.57%
| Total Collections (Invoices Paid) |  | 52156.916
| Cash Flow |  | 13316.916
Only complete the blue shaded areas